## Feuil1
SPRINT 1: SPRINT BACKLOG
User story | Id Task | Tasks | Effort in Hours | Remaining Hours
Team member: Jasser
As an healthcare manager I wish to add a patient to the healthcare system | 1.1.1 | Patient entity implementation
| 1.1.2 | Preparation of the patient add-in interface | 4 | 0
| 1.1.3 | Creating the patient add-in form | 1 | 1
| 1.1.4 | Coding the student add-in CRUD | 1 | 0
| 1.1.5 | Test the CRUD | 2 | 0
As an healthcare manager I wish to edit a patient details | 1.2.1 | Adding the feature in the display interface | 4 | 0
| 1.2.2 | Preparation of the patient edit interface | 1 | 1
| 1.2.3 | Creating the patient details edit form | 1 | 0
| 1.2.4 | Coding the patient details editing CRUD | 2 | 0
| 1.2.5 | Test the CRUD
|  |  | 4 | 0
As an healthcare manager I wish to consult the patients list | 1.3.1 | Preparation of the patients list interface | 1 | 0
| 1.3.2 | Coding the patients list display CRUD | 2 | 0
| 1.3.3 | Test the CRUD
|  |  | 4 | 0
As an healthcare manager I wish to delete a patient from the healthcare system | 1.4.1 | Adding the delete features in the display interface | 1 | 0
| 1.4.2 | Coding the patient deleting CRUD | 2 | 0
| 1.4.3 | Test the CRUD
2
|  |  | 4 | 0
As a healthcare manager I wish to add a patient medical record in the healthcare system | 1.5.1 | Adding the feature in the display interface | 1 | 0
| 1.5.2 | Preparation of the patient record adding interface | 2 | 0
| 1.5.3 | Coding the patient record adding CRUD | 3 | 0
| 1.5.4 | Creating the patient record adding form | 1 | 0
| 1.5.5 | Coding the student add-in CRUD | 1 | 0
| 1.5.6 | Test the CRUD
As a healthcare manager I wish to add a patient appointement to the healthcare system | 1.6.1 | Appointement entity implementation | 4 | 0
| 1.6.2 | Adding the feature in the display interface
| 1.6.3 | Preparation of the patient appointement interface | 1 | 1
| 1.6.4 | Creating the patient appointement add-in form | 1 | 0
| 1.6.5 | Coding the student appointement add-in CRUD | 2 | 0
| 1.6.6 | Test the CRUD
As a healthcare manager I wish to consult the patients' appointements list | 1.7.1 | Preparation of the patient's appointement details interface | 1 | 0
| 1.7.2 | Coding the patient details display CRUD
| 1.7.3 | Test the CRUD | 2 | 0
As an healthcare manager I wish to edit a patient's appointement details | 1.8.1 | Adding the feature in the display interface
| 1.8.2 | Preparation of the patient's appointement edit interface | 1 | 1
| 1.8.3 | Creating the patient details edit form | 1 | 0
| 1.8.4 | Coding the patient details editing CRUD | 2 | 0
| 1.8.5 | Test the CRUD
As an healthcare manager I wish to delete a patient's appointement from the healthcare system | 1.9.1 | Adding the feature in the display interface | 1 | 0
| 1.9.2 | Coding the patient's appointement deleting CRUD | 2 | 0
| 1.9.3 | Test the CRUD
As a doctor I wish to consult the patients' appointements list | 1.10.1 | Preparation of the patient's appointement details interface
| 1.10.2 | Coding the student details display CRUD
| 1.10.3 | Test the CRUD | 2 | 0
As a doctor I wish to consult the patients records list | 1.11.1 | Preparation of the patients records interface
| 1.11.2 | Coding the patients records display CRUD
| 1.11.3 | Test the CRUD | 2 | 0
As a doctor I wish to edit the patients records | 1.12.1 | Adding the feature in the display interface
| 1.12.2 | Preparation of the patient's record edit interface | 1 | 1
| 1.12.3 | Creating the record editing form | 1 | 0
| 1.12.4 | Coding the record editing CRUD | 2 | 0
| 1.12.5 | Test the CRUD
Team member: Fayrouz
As an education manager I wish to add a student to the education system | 2.1.1 | Student entity implementation
| 2.1.2 | Preparation of the student add-in interface | 4 | 0
| 2.1.3 | Creating the student add-in form | 1 | 1
| 2.1.4 | Coding the student add-in CRUD | 1 | 0
| 2.1.5 | Test the CRUD | 2 | 0
As an education manager I wish to edit a student details | 2.2.1 | Adding the feature in the display interface | 4 | 0
| 2.2.2 | Preparation of the student edit interface | 1 | 1
| 2.2.3 | Creating the student details edit form | 1 | 0
| 2.2.4 | Coding the student details editing CRUD | 2 | 0
| 2.2.5 | Test the CRUD
As an education manager I wish to have access to the list of all the students | 2.3.1 | Preparation of the students list interface | 3 | 0
| 2.3.2 | Coding the student list CRUD | 1 | 0
| 2.3.3 | Test the CRUD | 1 | 0
As an education manager I wish to delete students from the education system | 2.4.1 | Adding the feature in the display interface | 1 | 0
| 2.4.2 | Coding the student delete CRUD | 1 | 0
| 2.4.3 | Test the CRUD | 1 | 0
As an education manager I wish to add a study level to the education system | 2.5.1 | level entity implementation
| 2.5.2 | Preparation of the level add-in interface | 4 | 0
| 2.5.3 | Creating the level add-in form | 1 | 1
| 2.5.4 | Coding the level add-in CRUD | 1 | 0
| 2.5.5 | Test the CRUD | 2 | 0
As an education manager I wish to make a list of the levels the education system offers | 2.5.1 | Preparation of the levels list interface | 1 | 0
| 2.5.2 | Coding the levels list CRUD | 5 | 5
| 2.5.3 | Tester le code | 2 | 2
As an education manager I wish to edit a study level to the education system | 2.6.1 | Adding the feature in the display interface
| 2.6.2 | Preparation of the level editing interface | 4 | 0
| 2.6.3 | Creating the level editing form | 1 | 1
| 2.6.4 | Coding the level editing CRUD | 1 | 0
| 2.6.5 | Test the CRUD | 2 | 0
As an education manager I wish to delete a level from the education system | 2.7.1 | Adding the feature in the display interface | 1 | 0
| 2.7.2 | Coding the level deleting CRUD | 1 | 0
| 2.7.3 | Test the CRUD
As an education manager I wish to assign students to levels in the education system | 2.8.1 | Adding the feature in the levels display interface | 1 | 0
As an education manager I wish to search for a specified student in the education system | 2.8.2 | Adding the feature in the levels display interface | 1 | 0
As a teacherI wish to add coursesl to the education system | 2.9.1 | courses entity implementation
| 2.9.2 | Preparation of the courses add-in interface | 4 | 0
| 2.9.3 | Creating the cources add-in form | 1 | 1
| 2.9.4 | Coding the courses add-in CRUD | 1 | 0
| 2.9.5 | Test the CRUD | 2 | 0
As a teacher I wish to make a list of the courses the education system offers | 2.10.1 | Preparation of the courses list interface | 1 | 0
| 2.10.2 | Coding the courses list CRUD | 5 | 5
| 2.10.3 | Tester le code | 2 | 2
Team member: Khansa
As a staff manager I wish to add a staff member account to the system | 3.1.1 | staff entity implementation
| 3.1.2 | Preparation of the staff add-in interface | 4 | 0
| 3.1.3 | Creating the staff add-in form | 1 | 1
| 3.1.4 | Coding the staff add-in CRUD | 1 | 0
| 3.1.5 | Test the CRUD | 2 | 0
As a staff manager I wish to edit a staff member account details | 3.2.1 | Adding the feature in the display interface | 4 | 0
| 3.2.2 | Preparation of the staff editing interface | 1 | 1
| 3.2.3 | Creating the staff details editing form | 1 | 0
| 3.2.4 | Coding the staff details editing CRUD | 2 | 0
| 3.2.5 | Test the CRUD
As a staff manager I wish to consult the staff members list | 3.3.1 | Preparation of the staff list interface | 1 | 0
| 3.3.2 | Coding the staff list display CRUD | 2 | 0
| 3.3.3 | Test the CRUD
|  |  | 4 | 0
As a staff manager I wish to delete a staff member from the system | 3.4.1 | Adding the delete features in the display interface | 1 | 0
| 3.4.2 | Coding the staff deleting CRUD | 2 | 0
| 3.4.3 | Test the CRUD
As a staff member I wish to add a demand | 3.5.1 | Demand entity implementation
| 3.5.2 | Preparation of the demand add-in interface | 4 | 0
| 3.5.3 | Creating the demand add-in form | 1 | 1
| 3.5.4 | Coding the demand add-in CRUD | 1 | 0
| 3.5.5 | Test the CRUD | 2 | 0
As a staff member I wish to edit my account details | 3.6.1 | Adding the feature in the homepage interface | 4 | 0
| 3.6.2 | Preparation of the account editing interface | 1 | 1
| 3.6.3 | Creating the account details editing form | 1 | 0
| 3.6.4 | Coding the account details editing CRUD | 2 | 0
| 3.6.5 | Test the CRUD
As a staff manager I wish to consult my account | 3.7.1 | Adding the feature in the homepage | 4 | 0
| 3.7.2 | Preparation of the account interface | 1 | 1
| 3.7.3 | Coding the account consulting CRUD | 2 | 0
| 3.7.4 | Test the CRUD
As a shelterkeeper I wish to add a report | 3.8.1 | report entity implementation
| 3.8.2 | Preparation of the report add-in interface | 4 | 0
| 3.8.3 | Creating the report add-in form | 1 | 1
| 3.8.4 | Coding the report add-in CRUD | 1 | 0
| 3.8.5 | Test the CRUD | 2 | 0
As a shelterkeeper I wish to edit my reports | 3.8.1 | Adding the feature in the display interface | 4 | 0
| 3.8.2 | Preparation of the reports editing interface | 1 | 1
| 3.8.3 | Creating the reports editing form | 1 | 0
| 3.8.4 | Coding the reports editing CRUD | 2 | 0
| 3.8.5 | Test the CRUD
As a shelterkeeper I wish to consult my reportes list | 3.9.1 | Preparation of the reports list interface | 1 | 0
| 3.9.2 | Coding the reports list display CRUD | 2 | 0
| 3.9.3 | Test the CRUD
|  |  | 4 | 0
As a shelterkeeper I wish to consult the refugees list | 3.10.1 | Preparation of the refugees list interface | 1 | 0
| 3.10.2 | Coding the refugees list display CRUD | 2 | 0
| 3.10.3 | Test the CRUD
As a shelterkeeper I wish to edit refugees details | 3.11.1 | Adding the feature in the display interface | 4 | 0
| 3.11.2 | Preparation of the refugees details editing interface | 1 | 1
| 3.11.3 | Creating the refugees editing form | 1 | 0
| 3.11.4 | Coding the refugees editing CRUD | 2 | 0
| 3.11.5 | Test the CRUD
Team member: Chaima
As a warehouse manager I wish to add supplies | 4.1.1 | Supply entity implementation
| 4.1.2 | Preparation of the supplies add-in interface | 4 | 0
| 4.1.3 | Creating the supplies add-in form | 1 | 1
| 4.1.4 | Coding the supplies add-in CRUD | 1 | 0
| 4.1.5 | Test the CRUD | 2 | 0
As a warehouse manager I wish to edit supplies details | 4.2.1 | Adding the feature in the display interface | 4 | 0
| 4.2.2 | Preparation of the supplies editing interface | 1 | 1
| 4.2.3 | Creating the supplies editing form | 1 | 0
| 4.2.4 | Coding the supplies editing CRUD | 2 | 0
| 4.2.5 | Test the CRUD
As a warehouse manager I wish to consult the supplies list | 4.3.1 | Preparation of the supplies list interface | 1 | 0
| 4.3.2 | Coding the supplies list display CRUD | 2 | 0
| 4.3.3 | Test the CRUD
|  |  | 4 | 0
As a warehouse manager I wish to delete supplies from the system | 4.4.1 | Adding the delete features in the display interface | 1 | 0
| 4.4.2 | Coding the supplies deleting CRUD | 2 | 0
| 4.4.3 | Test the CRUD
As a warehouse manager I wish to search for supplies in the system | 4.5.1 | Adding the feature in the display interface | 4 | 0
| 4.5.2 | Preparation of the supplies searching interface | 1 | 1
| 4.5.3 | Creating the supplies searching form | 1 | 0
| 4.5.4 | Coding the supplies searching CRUD | 2 | 0
| 4.5.5 | Test the CRUD
Team member: Nada
As a registration manager I wish to add refugees to the system | 5.1.1 | refugee entity implementation
| 5.1.2 | Preparation of the refugees add-in interface | 4 | 0
| 5.1.3 | Creating the refugees add-in form | 1 | 1
| 5.1.4 | Coding the refugees add-in CRUD | 1 | 0
| 5.1.5 | Test the CRUD | 2 | 0
As a registration manager I wish to edit a refugee details | 5.2.1 | Adding the feature in the display interface | 4 | 0
| 5.2.2 | Preparation of the refugees editing interface | 1 | 1
| 5.2.3 | Creating the refugees editing form | 1 | 0
| 5.2.4 | Coding the refugees editing CRUD | 2 | 0
| 5.2.5 | Test the CRUD
As a registration manager I wish to consult the refugees list | 5.3.1 | Preparation of the refugees list interface | 1 | 0
| 5.3.2 | Coding the refugees list display CRUD | 2 | 0
| 5.3.3 | Test the CRUD
|  |  | 4 | 0
As a registration manager I wish to delete a refugee from the system | 5.4.1 | Adding the delete features in the display interface | 1 | 0
| 5.4.2 | Coding the refugees deleting CRUD | 2 | 0
| 5.4.3 | Test the CRUD
As a registration manager I wish to assing refugees a shelter | 5.5.1 | Adding the feature in the add-in interface | 1 | 0
| 5.5.2 | Coding the refugees assigning CRUD | 2 | 0
| 5.5.3 | Test the CRUD
As a camp manager I wish to consult the reportes list | 5.6.1 | Preparation of the reports list interface | 1 | 0
| 5.6.2 | Coding the reports list display CRUD | 2 | 0
| 5.6.3 | Test the CRUD
As a camp manager I wish to consult the demands list | 5.7.1 | Preparation of the demands list interface | 1 | 0
| 5.7.2 | Coding the demands list display CRUD | 2 | 0
| 5.7.3 | Test the CRUD
As a camp manager I wish to confirm demands | 5.8.1 | Adding the feature in the display interface | 4 | 0
| 5.8.2 | Coding the confirmation CRUD | 2 | 0
| 5.8.3 | Test the CRUD